## Assessment
Delivery Control Assessment
One row per control. Complete every column; a blank column is an unfinished assessment, not a neutral answer.
Start with the decision, not the control. See the Instructions sheet before filling this in.
Control | Decision enabled | Evidence | Finding that would change it | Owner | Review window | Verdict | Action
Example: weekly status report | None stated | No decision attached in twelve months | None | — | — | Monitoring | Rename
Portfolio summary
Excludes the amber example row.
Decision-grade | 0
Latent | 0
Monitoring | 0
Administration | 0
Controls assessed | 0

## Instructions
Delivery Control Assessment
Companion to the Knowledge Center template of the same name.
What this is
Purpose | A portfolio assessment. One row per control, one verdict each, one action each. The question is whether the set of controls produces the decisions leadership has to make, not whether a given control operates correctly.
Not this | Not a per-control checklist, not a governance checklist, not an audit. Nothing here verifies compliance or evidence quality.
How to fill it in
1. Start with the decision | Naming the control first invites a description of what it does, which is always available and never the point. Naming the decision first exposes the controls that inform none.
2. Evidence | What supports the verdict, not what the control does. Reach for the specific: duplicated the change log; exists because the regulator requires it; raised a finding nobody could action.
3. Finding | What would this control have to surface to change the decision? If nothing realistic would, the verdict is Monitoring, and that is an honest answer rather than a failing one.
4. Verdict | Follow the three answers. See the definitions below.
5. Action | Keep, Retire, Empower, or Rename. Empower is the one most often needed and least often chosen: a latent control usually needs an owner with authority, not removal.
No scoring | There is no score, no weighting, and no maturity level. A number would let two people record agreement they do not have, and a traffic light would let a control be amber for a year.
Verdicts
Decision-grade | All three questions answered. The control enables a named decision, could produce a finding that changes it, and reaches someone who can act in time.
Latent | The decision and finding are real, but nobody is empowered to act in time. The most dangerous category, because it looks identical to a decision-grade control from the outside.
Monitoring | No realistic finding would change the decision. Legitimate and useful when named as such. A control environment needs instruments.
Administration | No decision is served at all. The control exists because it was added, because it appears on a template, or because removing it would require a conversation nobody wants.
Column guidance
Control | The mechanism, named as the programme refers to it.
Decision enabled | The decision this control informs, and the person who makes it. Both named. Visibility is not a decision.
Evidence | What supports the verdict, not what the control does.
Finding that would change it | A concrete finding that would alter the decision. "None" is a legitimate and common answer.
Owner | The person who acts on a finding. A named person, not a forum and not a role nobody holds.
Review window | How long between a finding arising and action being possible.
Verdict | Decision-grade, Latent, Monitoring, or Administration.
Action | Keep, Retire, Empower, or Rename. One per row.
Filling this in
Type into the white rows on the Assessment sheet. The amber row is an example: overwrite or delete it. Verdict and Action are dropdown lists. The summary below the table counts verdicts automatically.

## Worked example
Worked example
Illustrative, constructed to show completed rows. Not drawn from a specific engagement; no outcomes are claimed.
Control | Decision enabled | Evidence | Finding that would change it | Owner | Review window | Verdict | Action
Weekly status report | None stated | No decision attached in twelve months | None | — | — | Monitoring | Rename
Steering committee | Continue and release funding, sponsor | Approved by default at last four meetings | Workstream cannot deliver in envelope | Sponsor | Monthly | Latent | Empower
Stage gate | Proceed to next phase, gate chair | Never failed since inception | Unmet exit criteria | Gate chair | Per phase | Latent | Empower
RAID log | None identified | Duplicated the change log | None | — | — | Administration | Retire
Benefits tracker | Adjust scope, business owner | Variance reported, no action taken | Widening benefits variance | Not assigned | Quarterly | Latent | Empower
Four of five rows need something other than removal. Three latent controls need owners with authority; one is genuinely administration. The portfolio does not need more controls.